## Gantt Chart
Team 6 Gantt chart
PROJECT TITLE |  | Bioreactor Controller Development |  | COMPANY NAME | [6 empty] | UCL Team 6
|  |  |  | DATE | [6 empty] | 16/11/2020
Phase Number | TASK TITLE | TASK OWNER | START DATE
|  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
|  |  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Initial Development
| Development of Thermal SS software | Pom | 16/11/20 | bar: WEEK 1 M
| Circuitry of Thermal SS | Leo | 16/11/20 | bar: WEEK 1 M to WEEK 1 W
| Development of stirring SS software | Pom | 17/11/20 | bar: WEEK 1 T to WEEK 1 T
| Circuitry of stirring SS | Emily | 19/11/20 | bar: WEEK 1 T to WEEK 1 F
| Development of pH SS software | Pom | 19/11/20 | bar: WEEK 1 T to WEEK 1 F
| Circuitry of pH SS | Zequan | 19/11/20 | bar: WEEK 1 W to WEEK 1 F
| Sensors & Actuators | Michael | 18/11/20 | bar: WEEK 1 W to WEEK 1 F
2 | Testing Phase 1
| Testing Software | CS | 23/11/20 | bar: WEEK 2 M to WEEK 2 F
| Testing Circuitry | EEE | 23/11/20 | bar: WEEK 2 M to WEEK 2 F
3 | System Development
| Development of Thermal SS software (Continued) | Pom | 30/11/20 | bar: WEEK 3 M to WEEK 3 T
| Circuitry of Thermal SS (Continued) | Leo | 30/11/20 | bar: WEEK 3 M to WEEK 3 W
| Development of stirring SS software (Continued) | Pom | 2020-01-12 | bar: WEEK 3 T to WEEK 3 W
| Circuitry of stirring SS (Continued) | Emily | 30/11/20 | bar: WEEK 3 M to WEEK 3 W
| Development of pH SS software (Continued) | Pom | 2020-03-12 | bar: WEEK 3 W to WEEK 3 T
| Circuitry of pH SS | Zequan | 30/11/20 | bar: WEEK 3 M to WEEK 3 W
| Develop UI | Filo | 30/11/20 | bar: WEEK 3 M to WEEK 3 F
4 | Final Test Phase
| Software Checks | Pom | 2020-07-12 | bar: WEEK 4 M to WEEK 4 T
| UI Checks | Filo | 2020-07-12 | bar: WEEK 4 M to WEEK 4 T
| Circuitry Checks | EEE | 2020-07-12 | bar: WEEK 4 M to WEEK 4 T
| Deliver final system | CS/EEE | 2020-11-12 | bar: WEEK 4 F